## Summary
Daily Report - Day 1 | [8 empty] | Hướng dẫn:
Date | 2022-08-16 | [7 empty] | 1. Save file trên GDrive, share cho team và GV ở email kim.nguyen.mt@gmail.com
Build | 0.9.8 | [7 empty] | 2. Test Lead hoàn thành sheet Summary, các ô màu hồng
3. Toàn team hoàn thành TCs và Bugs theo yêu cầu mỗi ngày.
Team 1 |  | Name | [6 empty] | Cách sửa bài
| - Test Lead | Trịnh Gia Khiêm | [6 empty] | 1. GV comment và tô màu vàng các ô cần sửa
| - Tester 1 | Bùi Quang Dũng | [6 empty] | 2. HV tự sửa bài theo comment của GV. Sau khi sửa xong thì tô màu xanh lên ô đó. Tất cả các ô màu vàng phải được sửa. Vào cuối ngày khi nộp bài không được để lại một ô màu vàng nào cả.
| - Tester 2 | Khưu Cẩm Tú | [6 empty] | 3. GV sẽ kiểm tra lại ô màu xanh, nếu Ok, GV sẽ đổi thành màu trắng, còn nếu vẫn chưa được thì GV sẽ tiếp tục comment và tô màu vàng lại.
| - Tester 3 | Nguyễn Văn Tài | [6 empty] | * Không "Resolved" hay Delete comment của GV nhé !!!
| - Tester 4 | Võ Thị Lộc
- Tester 5
Smoke Test |  | # | %
| Passed | 6 | 100%
| Failed | 0 | 0%
| Total: | 6 | 100%
TC List |  | # | %
| Passed | 10 | 58.82%
| Failed | 7 | 41.18%
| Total: | 17 | 100%
Bug Status |  | # | %
(Type in) | Open | 6 | 60%
| Closed as Valid | 0 | 0%
| Closed as Invalid | 4 | 40%
| Total: | 10 | 100%
Daily Report - Day 2
Date | 17/08/2022
Build | 0.9.9
Team 1 |  | Name
| - Test Lead | Bùi Quang Dũng
| - Tester 1 | Trịnh Gia Khiêm
| - Tester 2 |  | Khưu Cẩm Tú
| - Tester 3 |  | Nguyễn Văn Tài
| - Tester 4 | Võ Thị Lộc
- Tester 5
Smoke Test |  | # | %
| Passed | 5 | 83.33%
| Failed | 1 | 16.67%
| Total: | 6 | 100%
TC List |  | # | %
| Passed | 16 | 94.12%
| Failed | 7 | 41.18%
| Total: | 23 | 135.3%
Bug Status |  | # | %
(Type in) | Open | 14 | 56%
| Closed as Valid | 5 | 20%
| Closed as Invalid | 6 | 24%
| Total: | 25 | 100%
Build Progress
|  | 0.9.8 | 0.9.9
| # of TCs Created | 17 | 23
| # of Passed TCs | 10 | 16
| # of Failed TCs | 7 | 7
|  | 0.9.8 | 0.9.9
| # of Bugs found | 10 | 25
| # of Open Bugs | 6 | 14
| # of Closed Valid Bugs | 0 | 5
| # of Closed Invalid Bugs | 4 | 6
Daily Report - Day 3
Date | 19/08/2022
Build | 1.0.0
Team 1 |  | Name
| - Test Lead | Nguyễn Văn Tài
| - Tester 1 | Bùi Quang Dũng
| - Tester 2 |  | Trịnh Gia Khiêm
| - Tester 3 |  | Khưu Cẩm Tú
| - Tester 4 | Võ Thị Lộc
- Tester 5
Smoke Test |  | # | %
| Passed | 5 | 83.33%
| Failed | 1 | 16.67%
| Total: | 6 | 100%
TC List |  | # | %
| Passed | 25 | 147.1%
| Failed | 9 | 52.94%
| Total: | 34 | 200%
Bug Status |  | # | %
(Type in) | Open | 22 | 61.11%
| Closed as Valid | 5 | 13.89%
| Closed as Invalid | 9 | 25%
| Total: | 36 | 100%
Build Progress
|  | 0.9.8 | 0.9.9 | 1.0.0
| # of TCs Created | 17 | 23 | 34
| # of Passed TCs | 10 | 16 | 25
| # of Failed TCs | 7 | 7 | 9
|  | 0.9.8 | 0.9.9 | 1.0.0
| # of Bugs found | 10 | 25 | 36
| # of Open Bugs | 6 | 14 | 22
| # of Closed Valid Bugs | 0 | 5 | 5
| # of Closed Invalid Bugs | 4 | 6 | 9
Team Statistic
Name | # of TCs Created | # of TCs Executed | # of Reviewed TCs | Urgent | High | Medium | Low | # of Reviewed Bugs | # of Regressed 1 | # of Regressed 2 | Scoring
Tú | 5 | 12 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 120
Lộc | 7 | 9 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 127
Tài | 6 | 9 | 5 | 0 | 2 | 4 | 0 | 5 | 1 | 0 | 149
Dũng | 8 | 16 | 6.5 | 0 | 1 | 4 | 1 | 7.5 | 0 | 0 | 209.5
Khiêm | 5 | 27 | 8.5 | 0 | 2 | 1 | 2 | 5 | 0 | 4 | 240
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Test Case List
Test Case List
TC ID | TC Description | Pre-Condition | Steps | Expected Result | Status | Created by | Created Date | Reviewed by | Build 0.9.8 |  | Build 0.9.9 |  | Build 1.0.0 |  | Notes
[9 empty] | Test Result | Executed by | Test Result | Executed by | Test Result | Executed by
SMOKE TEST |  |  |  |  | Open
REG-01 | Verify that user can create an account successfully with valid information. |  | 1. Navigate to Railway Website. 2. Select 'Register' tab. 3. Fill in requested fields with valid information. 4. Click 'Register' button. | User can create an account successfully with valid information. | Open | Tu | 15/08/2022 | Khiêm | Passed | Tú | Failed | Tú | Failed | Khiêm | Bug ID-17
LGI-01 | Verify that user can login. |  | 1. Open Website. 2. Select Login tab. 3. Enter valid email. 4. Enter valid password. 5. Click Login button. | User can login successfully. | Open | Lộc | 15/08/2022 | Khiêm | Passed | Lộc | Passed | Lộc | Passed | Khiêm
MTK-01 | Verify that user can see My Ticket tab | User has booked at least 1 ticket | 1. Navigate to QA Railway Website 2. Login with account has booked ticket 3. Select My ticket tab | User can see My ticket tab | Open | Tài | 15/08/2022 | Khiêm | Passed | Tài | Passed | Tài | Passed | Khiêm
MTK-02 | Verify that user can cancel booked tickets successfully | User booked tickets which are not expried | 1. Navigate to Railway Website. 2. Login with an account successfully 3. Select 'My ticket' tab. 4. Click 'Cancel' button. | User can cancel booked tickets successfully | Open | Tu | 15/08/2022 | Khiêm | Passed | Tu | Passed | Tài | Passed | Khiêm
BTK-01 | Vertify that user can book tickets successfully. |  | 1. Navigate to QA Railway Website. 2. Login with valid email and password. 3. Go to 'Book ticket' page. 4. Input valid information to all fields. 5. Click on 'Book ticket' button. | User can book tickets successfully. | Open | Dũng | 15/08/2022 | Khiêm | Passed | Dũng | Passed | Tú | Passed | Khiêm
LGI-02 | Verify that user can logout successfully. |  | 1. Navigate to Railway Website. 2. Login with an account successfully. 3. Select 'Logout' tab. | User can logout successfully | Open | Tu | 15/08/2022 | Khiêm | Passed | Tú | Passed | Tú | Passed | Khiêm
REGISTER
REG-02 | Verify that an confirmation email is sent to user when creating an account successfully |  | 1. Navigate to Railway Website. 2. Select 'Register' tab. 3. Fill in requested fields with valid information. 4. Click button 'Register' button. 5. Wait an email to confirm account. | An response email is sent for user to confirm account. | Open | Tu | 15/08/2022 | Khiêm | Failed | Tú | Skipped |  | Skipped |  | BugID-6
REG-03 | Verify that user can not book tickets without confirming account . |  | 1. Navigate to Railway Website. 2. Select 'Register' tab. 3. Fill in requested fields with valid information. 4. Click button 'Register' button. 5. Select 'Book ticket' tab. 6. Select valid information in all drop-downs to book ticket. 7. Click 'Book ticket' button. | User can not book tickets without confirming account. | Closed | Tu | 15/08/2022 | Khiêm | Failed | Tú | Skipped |  | Skipped |  | BugID-7
REG-04 | Verify that user can not register with invalid email . |  | 1. Navigate to Railway2 Website. 2. Click on 'Register' tab. 3. Fill in requested fields with valid information. 4. Fill in Email textbox with invalid email such as "khiem!@#$@gmail.com" 5. Click on Register button | User can not register with invalid email | Open | Khiêm | 17/08/2022 | Dũng |  |  | Failed | Khiêm | Skipped |  | BugID-22
REG-05 | Verify that user can not create an account when user logged in already. |  | 1. Navigate to Railway Website. 2. Login with valid account successfully. 3. Select 'FAQ' tab. 4. Click 'create an account' link in the first answer. | User can not create an account when user logged in already. | Open | Tú | 20/08/2022 | Tài |  |  |  |  | Passed | Tú
LOGIN
LGI-03 | Verify that error message when logging in with blank username |  | 1. Navigate to Railway Website. 2. Select Login tab . 3. Leave blank username text box. 4. Enter valid password. 5. Click Login button. | Error message when logging in with blank username | Open | Lộc | 15/08/2022 | Khiêm | Passed | Lộc | Skipped |  | Passed | Khiêm
LGI-04 | Verify that error message when logging in with blank password |  | 1. Navigate to Railway Website. 2. Select Login tab. 3. Enter valid email. 4. Leave blank password text box. 5. Click Login button. | Error message when logging in with blank passwork | Open | Lộc | 15/08/2022 | Khiêm | Passed | Lộc | Skipped |  | Passed | Khiêm
LGI-05 | Verify that error message when logging in with invalid email /password. |  | 1. Navigate to Railway Website. 2. Select Login tab. 3. Enter invalid email or/and password. 4. Click Login button. | Error message when logging in with invalid email / passwork. | Open | Lộc | 15/08/2022 | Khiêm | Passed | Lộc | Skipped |  | Passed | Khiêm
LGI-06 | Verify that user can't copy and paste html tag in username and password |  | 1. Navigate to Railway Website. 2. Select Login tab. 3. copy and paste infomation such as: email:" <body> sitojo9363@offsala.com </body>" password:" 123 " 4. Click Login button. | Textbox does not allow to paste html tag | Open | Tài | 17/08/2022 | Dũng |  |  | Failed | Tài | Failed | Khiêm | BUGID#20
LGI-07 | Verify that user can't enter html tag in username and password |  | 1. Navigate to Railway Website. 2. Select Login tab. 3. Enter infomation such as: email:" <body> sitojo9363@offsala.com </body>" password:" 123 " 4. Click Login button. | Textbox does not allow to type html tag such as can't type character "<" and "> " | Open | Tài | 17/08/2022 | Dũng |  |  | Passed | Tài | Passed | Khiêm
LGI-08 | Verify that user can reset password with email address associated |  | 1. Navigate to QA Railway2 Website. 2. Click on Login tab 3. Click on 'Forgot Password page' 4. Fill the textbox with registered email 5. Click on 'Send Instructions' button | User receives password reset instructions to the email address associated with your account. | Open | Khiêm | 17/08/2022 | Dũng |  |  | Failed | Khiêm | Failed | Khiêm | bug ID:16
BOOK TICKET
BTK-02 | Verify that error message displays when user choose same depart and arrive station. |  | 1. Navigate to QA Railway Website. 2. Login with valid email and password. 3. Go to 'Book ticket' page. 4. Choose the same station with 'Depart from' and 'Arrive at' combo box. 5. Choose all other combox. 5. Click on 'Book ticket' button. | Show the error message' Depart and Arrive stations can't be the same'. | Open | Dũng | 15/08/2022 | Khiêm | Passed | Dũng | Passed | Tài | Passed | Khiêm | Can't choose the same depart and arrive station.
BTK-03 | Verify that the seat selection page appears when user click on 'Book ticket' button. |  | 1. Navigate to QA Railway Website. 2. Login with valid email and password. 3. Go to 'Book ticket' page. | The seat selection page appears. | Closed | Dũng | 15/08/2022 | Khiêm | Failed | Dũng |  |  |  |  | Bug ID:3 Close as limited fearture
BTK-04 | Verify that user can choose seat when booking tickets. |  | 1. Navigate to QA Railway Website. 2. Login with valid email and password. 3. Go to 'Book ticket' page. 5. Choose all combox. 6. Click on 'Book ticket' button. | users can choose seats according to the number of tickets booked. | Closed | Dũng | 15/08/2022 | Khiêm | Failed | Dũng |  |  |  |  | Bug ID:3
BTK-05 | Verify that user can choose departure day when booking tickets. |  | 1. Navigate to QA Railway Website. 2. Login with valid email and password. 3. Go to 'Book ticket' page. 4. Choose the combo box 'Depart day' 5. Choose all other combox. 6. Click on 'Book ticket' button. | user can choose departure day | Open | Khiêm | 20/08/2022 | Tài |  |  |  |  | Passed | Khiêm
BKT-06 | Verify that user can book ticket for 3-30 days ahead. |  | 1. Navigate to QA Railway Website. 2. Login with valid email and password. 3. Go to 'Book ticket' page. 4. Choose the combo box 'Depart day' | user can book ticket for 3-30 days ahead. | Open | Khiêm | 20/08/2022 | Tài |  |  |  |  | Failed | Khiêm | Bug ID: 36
MY TICKET
MTK-03 | Verify that user can see departure time | User has booked at least 1 ticket | 1. Navigate to QA Railway Website 2. Login with account has booked ticket 3. Click My ticket tab | User can see departure time | Open | Tài | 15/08/2022 | Khiêm | Failed | Tài | Failed | Khiêm | Passed | Khiêm | BugID 9
MTK-04 | Verify that user can see estimated time of arrival | User has booked at least 1 ticket | 1. Navigate to QA Railway Website 2. Login with account has booked ticket 3. Click My ticket tab | User can see estimated time of arrival | Open | Tài | 15/08/2022 | Khiêm | Failed | Tài | Failed | Khiêm | Passed | Khiêm | BugID 10
MTK-05 | Verify that confirmation message displays when user cancel their ticket | User has booked at least 1 ticket | 1. Navigate to QA Railway Website 2. Login with account has booked ticket 3. Click My ticket tab 4. Select ticket user want to cancel 5. Click Cancel button | Confirmation message display when user cancel ticket | Open | Tài | 15/08/2022 | Khiêm | Failed | Tài | Passed | Khiêm | Passed | Khiêm | BugID 8
MTK-06 | Verify that when there are 6 or more rows, the filter appears | User has booked at least 6 times | 1. Navigate to QA Railway Website 2. Login with account has booked ticket 3. Click My ticket tab | when there are 6 or more rows, the filter appears | Open | Lộc | 17/08/2022 | Dũng |  |  | Passed | Lộc | Passed | Khiêm
MTK-07 | Verify that confirmation user can contact admin for payment | User has booked at least 1 ticket | 1. Navigate to QA Railway Website 2. Login with account has booked ticket | User can contact admin for payment | Closed | Lộc | 17/08/2022 | Dũng |  |  | Passed | Lộc | Passed | Khiêm
MTK-08 | Verify that user can delete their expired Tickets | Ticket that user has booked be expired | 1. Navigate to QA Railway Website. 2. Login with valid email and password. 3. Go to 'My ticket' page. 5. Click on 'Delete button. | user can delete their expired tickets | Open | Dũng | 17/08/2022 | Dũng |  |  | Passed | Dũng | Passed | Khiêm
CHANGE PASSWORD
PWD-01 | Verify that user can not change password successfully with wrong current password |  | 1. Navigate to Railway Website. 2. Login with valid account successfully. 3. Select 'Change password' tab. 4. Input wrong current password, valid new password and right confirmation password. 5. Click 'Change Password' button. | User can not change password successfully with wrong current password. | Open | Tú | 17/08/2022 | Dũng |  |  | Passed | Tú | Passed | Dũng
PWD-02 | Verify that user can not change password successfully when confirmation password does not match with new password. |  | 1. Navigate to Railway Website. 2. Login with valid account successfully. 3. Select 'Change password' tab. 4. Input right current password, valid new password and wrong confirmation password. 5. Click 'Change Password' button. | User can not change password successfully when confirmation password does not match with new password. | Open | Tú | 17/08/2022 | Dũng |  |  | Passed | Tú | Passed | Dũng
PWD-03 | Verify that user can not change password successfully when one of the fields is blank |  | 1. Navigate to Railway Website. 2. Login with valid account successfully. 3. Select 'Change password' tab. 4. Do not fill in one of the fields. 5. Click 'Change Password' button. | User can not change password successfully when one of the fields is blank. | Open | Tú | 17/08/2022 | Dũng |  |  | Passed | Tú | Passed | Dũng
PWD-04 | Verify that user can't change password without input any information |  | 1. Navigate to QA Railway website. 2. Login with valid information. 3. Go to 'Change Password' page. 4. Click on 'Change Password' button. | user can't change password without input any information | Open | Dũng | 17/08/2022 | Dũng |  |  | Passed | Dũng | Passed | Dũng
PWD-05 | Verify that warning message displays when user inputs new password same as current password. |  | 1. Navigate to Railway Website. 2. Login with valid account successfully. 3. Select 'Change password' tab. 4. Input new password and confirmation password same as valid current password. 5. Click 'Change Password' button. | Warning message displays when user input new password same as current password. | Open | Tú | 20/08/2022 | Tài |  |  |  |  | Failed | Tú
TICKET PRICE
TKP-01 | Verify that users can book the type of seat to book tickets in ticket price |  | 1. Navigate to Railway2 Website. 2. Login with registered email and password 3. Select 'Ticket Price' tab. 4. Select 'Check Price' 5. Choose type of seat by click on 'Book Ticket' | The same type of seat has been booked in 'Book ticket form' | Open | Khiêm | 17/08/2022 | Dũng |  |  | Passed | Khiêm | Passed | Dũng
TKP-02 | Verify that there is a combo box for user to choose type of seat |  | 1. Navigate to QA Railway Website. 2. Select 'Ticket Price' tab.' | there is a combo box for user to choose type of seat | Closed | Dũng | 17/08/2022 | Dũng |  |  | Failed | Dũng
TKP-03 | Verify that depart station and arrive station information when booking the ticket matching the information on My ticket |  | 1. Navigate to Railway Website 2. Login with registered email and password 5. Click on Book ticket 6. Choose ticket from Book ticket form 7. Click Book ticket button | Depart station and arrive station information when booking the ticket matching the information on My ticket | Open | Lộc | 20/08/2022 | Tài |  |  |  |  | Passed | Lộc
TKP-04 | Verify that the ticket price in Ticket Price matching the ticket price in My ticket |  | 1. Navigate to Railway Website 2. Login with registered email and password 3. Select 'Ticket Price' tab 4. Click on Check Price 5. Click on Book ticket 6. Choose ticket from Book ticket form 7. Click on Book ticket button 8. Click on My ticket | The ticket price in Ticket Price matching the ticket price in My ticket | Open | Lộc | 20/08/2022 | Tài |  |  |  |  | Passed | Lộc
TIMETABLE
TTB-01 | Verify that there is a filter to filter the 'Depart Station' in the timetable. |  | 1. Navigate to QA Railway Website. 2. Go to 'Timetable'page | there is a filter to filter the 'Depart Station' in the timetable | Open | Dũng | 21/08/2022 | Tài |  |  |  |  | Failed | Dũng
TTB-02 | Verify that there is a filter to filter the 'Arrive Station' in the timetable. |  | 1. Navigate to QA Railway Website. 2. Go to 'Timetable'page | there is a filter to filter the 'Arrive Station' in the timetable | Open | Dũng | 21/08/2022 | Tài |  |  |  |  | Failed | Dũng
TTB-03 | Verify that there is a filter to filter the 'Depart Time' in the timetable. |  | 1. Navigate to QA Railway Website. 2. Go to 'Timetable'page | there is a filter to filter the 'Depart Time' in the timetable | Open | Dũng | 21/08/2022 | Tài |  |  |  |  | Failed | Dũng
TTB-04 | Verify that there is a filter to filter the 'Arrive Time' in the timetable. |  | 1. Navigate to QA Railway Website. 2. Go to 'Timetable'page | there is a filter to filter the 'Arrive Time' in the timetable | Open | Dũng | 21/08/2022 | Tài |  |  |  |  | Failed | Dũng

## Bug List
Bug List |  |  | Open | 21
|  |  | Closed as Valid | 5
|  |  | Closed as Invalid | 9
ID | Summary | Description | Steps to Reproduce (Including Expected Behaviour and Observed Behaviour) | Build found | Date found | Reproducibility | Severity | Frequency | Priority | Keyword | Resolution | Status | Build fixed | Reported by | Reviewed by | 0.9.9 Regressed by | 1.0.0 Regressed by | Note
1 | First name and Last name allow entering special characters |  | 1. Navigate to QA Railway Website. 2. Select 'Register' tab. 3. Fill in requested fields with valid information. 4. Enter special characters in First name and Last name . Expected Result: do not allow entering special characters in First name and Last name text box. Observed Result: First name and Last name allow entering special characters | 0.9.8 | 15/08/2022 | Always | Major | Sometimes | High | Register | To Be Fixed | Open |  | Lộc | Khiêm
2 | Phone number allows typing characters |  | 1. Navigate to QA Railway Website. 2. Select 'Register' tab. 3. Fill in requested fields with valid information. 4. Enter letters in Phone number text box Expected Result: do not allow entering letters in Phone number box. Observed Result: Phone number allows typing characters | 0.9.8 | 15/08/2022 | Always | Major | Sometimes | High | Register | To Be Fixed | Open |  | Lộc | Khiêm
3 | there should be a seat selection page when users book ticket. | The page lets users book ticket(s) successfully without choosing their seat(s), user can't find out the number of the seat(s) they will sit down at next ticket information page | 1. Navigate to QA Railway Website. 2. Login with valid email and password. 3. Go to 'Book ticket' page. 5. Choose all combox. 5. Click on 'Book ticket' button. Expected Result: There will be a seat selection page for users to choose their seat(s) based on their booked ticket(s). Observed Result: A page appears with the message 'Ticket booked successfully!' and display the ticket information. | 0.9.8 | 15/08/2022 | Always | Major | Everytime | High | Book Ticket | Not a Problem | Closed as Invalid |  | Dũng | Khiêm |  |  | BTK-03 BTK-04
4 | There is no combox box to choose Departure time. | The page just have combo box to choose the Depart day, no have combo box to choose Departure time. | 1. Navigate to QA Railway Website. 2. Login with valid email and password. 3. Go to 'Book ticket' page. Expected Result: There will be a combo box for users to choose Departure time. Observed Result: There is no combox box to choose Departure time. | 0.9.8 | 15/08/2020 | Always | Major | Everytime | High | Book Ticket | To Be Fixed | Open |  | Dũng | Khiêm
5 | There is no radio button to choose one-way or round-trip ticket | it is a missing function that will help users to book their departure and return ticket(s) in one booking. | 1. Navigate to QA Railway Website. 2. Login with valid email and password. 3. Go to 'Book ticket' page. Expected Result: There will be radio button for users to choose one-way or round-trip ticket(s). Observed Result: "There is no radio button to choose one-way or round-trip ticket(s). | 0.9.8 | 15/08/2022 | Always | Minor | Everytime | Medium | Book Ticket | To Be Fixed | Open |  | Dũng | Khiêm
6 | No response email is sent to user regarding account confirmation when user create an account successfully. | The register page of website provides information that user needs to confirm account after creating account successfully. However, no response email is sent to user regarding account confimation. | 1. Navigate to Railway Website. 2. Select 'Register' tab. 3. Fill in requested fields with valid information. 4. Click button 'Register' button. 5. Wait for an response email to confirm account. | 0.9.8 | 15/08/2022 | Always | Critical | Everytime | Urgent | Register | To Be Fixed | Open |  | Tú | Khiêm |  |  | REG-02
7 | User can book tickets successfully with unconfirmed account. | After user creates an account successfully, the website logins automatically by this account. So user can book tickets successfully without confirming account. | 1. Navigate to Railway Website. 2. Select 'Register' tab. 3. Fill in requested fields with valid information. 4. Click 'Register' button. 5. Select 'Book ticket' tab. 6. Select valid information in all drop-downs to book ticket. 7. Click 'Book ticket' button. | 0.9.8 | 15/08/2022 | Always | Critical | Everytime | Urgent | Register | Not a Problem | Closed as Invalid |  | Tú | Khiêm |  |  | REG-03
8 | No confirmation message display when user cancel ticket |  | 1. Navigato QA Raily Website 2. Login with account has booked ticket 3. Click My ticket tab 4. Select ticket user want to cancel 5. Click Delete Expected Result: Confirmation message display such as " Are you sure to cancel ticket ? " Observed Result: No Confirmation message display | 0.9.8 | 15/08/2022 | Always | Major | Everytime | Medium | My Ticket | Passed Verification | Closed as Valid | 0.9.9 | Tài | Khiêm | Tài |  | MTK-05
9 | There is no information about departure time in My Ticket tab |  | 1. Navigato QA Raily Website 2. Login with account has booked ticket 3. Click My ticket tab Expected Result: User can see departure time Observed Result: No information about departure time in My Ticket tab | 0.9.8 | 15/08/2022 | Always | Major | Everytime | Medium | My Ticket | To Be Fixed | Open |  | Tài | Khiêm |  |  | MTK-03
10 | There is no information about estimated time of arrival in My Ticket tab |  | 1. Navigato QA Raily Website 2. Login with account has booked ticket 3. Click My ticket tab Expected Result: User can see estimated time of arrival Observed Result: No information about estimated time of arrival in My Ticket tab | 0.9.8 | 15/08/2022 | Always | Major | Everytime | Medium | My Ticket | To Be Fixed | Open |  | Tài | Khiêm |  |  | MTK-04
11 | should give clear error message when canceling booked tickets |  | 1. Navigato QA Raily Website. 2. Login with account has booked ticket 3. Click My ticket tab Expected Result: message "are you sure to cancel the booked ticket?" Observed Result: message "http://railway2.csc.edu.vn/ cho biết: are you sure?" | 0.9.9 | 17/08/2022 | Always | Major | Sometimes | Medium | My Ticket | Not a Problem | Closed as Invalid |  | Lộc | Dũng
12 | When click on the 'Hủy' function on the message, the ticket will also be canceled |  | 1. Navigato QA Railway Website. 2. Login with account has Booked ticket 3. Click My ticket tab 4. Click on the Cancel of Manage ticket. 5. Click 'Hủy' on message box Expected Result: do not cancel the ticket when clicking "Hủy" Observed Result: Canceled when clicking "Hủy". | 0.9.9 | 17/08/2022 | Always | Major | Sometimes | Medium | My Ticket | Passed Verification | Closed as Valid | 1.0.0 | Lộc | Dũng |  | Khiêm
13 | When click on 'Cancel' function on the Manage ticket, the ticket will also be canceled |  | 1. Navigato QA Railway Website. 2. Login with account has Booked ticket 3. Click My ticket tab 4. Click on the Cancel of Manage ticket. 5. Leave to another page 6. Back to My ticket page Expected Result: the number of tickets remains the same Observed Result: the ticket has been deleted | 0.9.9 | 17/08/2022 | Always | Major | Sometimes | Medium | My Ticket | Not a Problem | Closed as Invalid |  | Lộc | Dũng
14 | spelling mistake about "Quảng Ngãi" destination |  | 1. Navigate to QA Railway2 Website. 2. Click on Ticktet price Expected Result: Right spelling "Quảng Ngãi" destination Observed Result: Wrong spelling " Quảng Ngải" destination | 0.9.9 | 17/08/2022 | Always | Minor | Sometimes | Low | View Ticket | To Be Fixed | Open | 0.9.9 | Khiêm | Dũng
15 | spelling mistake about "Đà Nẵng" destination |  | 1. Navigate to QA Railway2 Website. 2. Click on Ticket price Expected Result: Right spelling "Đà Nẵng" destination Observed Result: Wrong spelling " Đà Nẳng" destination | 0.9.9 | 17/08/2022 | Always | Minor | Sometimes | Low | View Ticket | To Be Fixed | Open | 0.9.9 | Khiêm | Dũng
16 | User can not reset password with email address associated |  | 1. Navigate to QA Railway2 Website. 2. Click on Login tab 3. Click on 'Forgot Password page' 4. Fill the textbox with registered email 5. Click on 'Send Instructions' button Expected Result: User can reset password with email address associated Observed Result: such as screenshot | 0.9.0 | 17/08/2022 | Always | Major | Sometimes | High | Login | To Be Fixed | Open |  | Khiêm | Dũng |  |  | LGI-08
17 | User can not create an account successfully with valid information. | When user creates an account, the website displays errors as attached bug screenshot. However, when user re-register , the website informs that the email address is already in use for register. In spite of that, user can not login with this email. | 1. Navigate to Railway Website. 2. Select 'Register' tab. 3. Fill in requested fields with valid information. 4. Click 'Register' button. Expected Result: User can create an account successfully with valid information. Observed Result: User can not create an account successfully with valid information. | 0.9.9 | 17/08/2022 | Always | Critical | Everytime | Urgent | Register | To Be Fixed | Open |  | Tú | Dũng |  |  | REG-01
18 | There should be display username instead of email |  | 1. Navigate to Railway Website. 2. Select Login tab. 3.Login with valid account | 0.9.9 | 17/08/2022 | Always | Minor | Everytime | Medium | Login | Not a Problem | Closed as Valid |  | Tài | Dũng
19 | There should be have date time picker to filter depature date in My ticket tab |  | 1. Navigato QA Raily Website 2. Login with valid account 3. Click Book Ticket tab and book 6 ticket successfully 4. Click My Ticket tab Expected Result: User can see choose depature time in date time picker to filter Observed Result: No date time picker to choose depature time | 0.9.9 | 17/08/2022 | Always | Major | Everytime | High | My Ticket | To Be Fixed | Open |  | Tài | Dũng
20 | user can copy and paste html tag in username and password | After click Login button with information about html tag, the website displays errors as attached bug screenshot. | 1. Navigate to Railway Website. 2. Select Login tab. 3. copy and paste infomation such as: email:" <body> sitojo9363@offsala.com </body>" password:" 123 " 4. Click Login button. Expected Result: Textbox does not allow to paste html tag Observed Result: Textbox allow to paste html tag | 0.9.9 | 17/08/2022 | Always | Major | Sometimes | High | Login | Failed Verification | Open |  | Tài | Dũng |  | Khiêm | LGI-06 Regression failed on Build 0.9.9
21 | no other departure date selection except the dates available in the combo box. |  | 1. Navigate to QA Railway Website. 2. Login with valid email and password. 3. Go to 'Book ticket' page. Expected Result: There will be more and more departure dates for user to choose when booking. Observed Result: There is no more and more departure dates for user to choose when booking. | 0.9.9 | 17/08/2022 | Always | Minor | Sometimes | Medium | Book Ticket | Not a Problem | Closed as Invalid |  | Dũng | Dũng
22 | user can register with invalid email |  | 1. Navigate to Railway2 Website. 2. Click on 'Register' tab. 3. Fill in requested fields with valid information. 4. Fill in Email textbox with invalid email 5. Click on Register button Expected Result: User can not register with invalid email Observed Result: User can register with invalid email such as Screenshot | 0.9.8 | 17/08/2022 | Intermittent | Major | Sometimes | High | Register | To Be Fixed | Open |  | Khiêm | Dũng |  |  | 2 bug: bug đăng ký ko thành công nhưng vẫn hiện email đã dùng, bug còn lại là cho phép nhập email không đúng định dạng REG-04
23 | the ticket still can cancel when user click on 'Hủy' in confirm message box |  | "1. Navigate to Railway2 Website. 2. Click on 'My Ticket' tab. 3. Click on 'Cancel' to cancel a ticket 4. Click on 'Hủy' in notification message Expected Result: the ticket can't be canceled Observed Result: the ticket is canceled such as Screenshot" | 0.9.9 | 17/08/2022 | Always | Major | Sometimes | High | My Ticket | Duplicate | Closed as Invalid |  | Khiêm | Dũng
24 | Current filter is lost after deleting a ticket |  | 1. Navigate to Railway website. 2. Login with valid information 3. Book some separate tickets 4. Adjust 3 days 5. Go to 'My ticket' page. 6. Use filter to filter any item. 7. Delete 1 ticket Expected Result: Current filter remains after ticket deletion. Observed Result: Current filter is lost after deleting a ticket. | 0.9.9 | 17/08/2022 | Always | Minor | Sometimes | Low | My Ticket | Passed Verification | Closed as Valid | 1.0.0 | Dũng | Dũng |  | Khiêm
25 | Current filter is lost after canceling a ticket |  | 1. Navigate to Railway website. 2. Login with valid information 3. Book some separate tickets. 4. Go to 'My ticket' page. 5. Use filter to filter any item. 6. Cancel 1 ticket Expected Result: Current filter remains after ticket cancellation. Observed Result: Current filter is lost after canceling a ticket. | 0.9.9 | 17/08/2022 | Always | Minor | Sometimes |  |  | Passed Verification | Closed as Valid | 1.0.0 | Dũng | Dũng |  | Khiêm
26 | User can access Login page after logged in already by pasting URL into a new tab in the same web browser. |  | 1. Navigate to Railway Website. 2. Login with valid account successfully. 3. Copy the link in the address bar. 4. Paste this link into a new tab in the same web browser. Expected Result: User can not access Login page by pasting URL after logged in already. Observed Result: User can access Login page by pasting URL into a new tab in the same web browser after logged in already. | 1.0.0 | 20/08/2022 | Always | Minor | Sometimes | Medium | Login | Not a Problem | Closed as Invalid | 1.0.0 | Tú | Tài
27 | User can access My Ticket page without logging in by pasting URL into a new tab in the same web browser. |  | 1. Navigate to Railway Website. 2. Login with valid account successfully. 3. Copy the link in the address bar. 4. Paste this link into a new tab in the same web browser. 5. Select 'My ticket' tab. Expected Result: User can not access My Ticket page by pasting URL without logging in. Observed Result: User can access My Ticket page by pasting URL into a new tab in the same web browser without logging in. | 1.0.0 | 20/08/2022 | Always | Minor | Sometimes | Medium | My Ticket | To Be Fixed | Open | 1.0.0 | Tú | Tài
28 | There should be a place to user can update and edit user information |  | 1. Navigate to Railway Website. 2. Login with valid account successfully. Expected Result: user can update and edit user information Observed Result: user can't update and edit user information | 1.0.0 | 20/08/2022 | Always | Minor | Hardly | Medium | Other | To Be Fixed | Open |  | Lộc | Tài
30 | There is Hue - Nha Trang routing but no Nha Trang - Hue routing |  | 1. Navigate to Railway Website. 2. Login with valid account successfully. 3. Click Timetable tab Expected Result: There is Nha Trang - Hue routing Observed Result: There isn't Nha Trang - Hue routing | 1.0.0 | 20/08/2022 | Always | Major | Sometimes | Medium | Other | To Be Fixed | Open |  | Lộc | Tài
31 | Unknown Error appears when user navigate to QA Railway Website. | See Bug Screenshot | 1. Navigate to QA Railway Website | 1.0.0 | 21/08/2022 | Intermittent | Major | Sometimes | Medium | Other | Need More Information | Open |  | Dũng | Tài
32 | There shoud be a filter to filter the 'Depart Station' in the timetable. |  | 1. Navigate to QA Railway Website. 2. Go to 'Timetable'page Expected Result: There will be a filter to filter the 'Depart Station' in the timetable. Observed Result: There isn't a filter to filter the 'Depart Station' in the timetable. | 1.0.0 | 21/08/2022 | Always | Minor | Everytime | Medium | Other | To Be Fixed | Open |  | Dũng | Tài
33 | There shoud be a filter to filter the 'Arrive Station' in the timetable. |  | 1. Navigate to QA Railway Website. 2. Go to 'Timetable'page Expected Result: There will be a filter to filter the 'Arrive Station' in the timetable. Observed Result: There isn't a filter to filter the 'Arrive Station' in the timetable. | 1.0.0 | 21/08/2022 | Always | Minor | Everytime | Medium | Other | To Be Fixed | Open |  | Dũng | Tài
34 | There shoud be a filter to filter the 'Depart Time' in the timetable. |  | 1. Navigate to QA Railway Website. 2. Go to 'Timetable'page Expected Result: There will be a filter to filter the 'Depart Time' in the timetable. Observed Result: There isn't a filter to filter the 'Depart Time' in the timetable. | 1.0.0 | 21/08/2022 | Always | Minor | Everytime | Medium | Other | Not a Problem | Closed as Invalid |  | Dũng | Tài
35 | There shoud be a filter to filter the 'Arrive Time' in the timetable. |  | 1. Navigate to QA Railway Website. 2. Go to 'Timetable'page Expected Result: There will be a filter to filter the 'Arrive Time' in the timetable. Observed Result: There isn't a filter to filter the 'Arrive Time' in the timetable. | 1.0.0 | 21/08/2022 | Always | Minor | Everytime | Medium | Other | Not a Problem | Closed as Invalid |  | Dũng | Tài
36 | user can not book ticket for 3-30 days ahead. |  | "1. Navigate to QA Railway Website. 2. Login with valid email and password. 3. Go to 'Book ticket' page. 4. Choose the combo box 'Depart day' Expected Result: user can book ticket for 3-30 days ahead. Observed Result: user only can book ticket for 3-28 days ahead. | 1.0.0 | 21/08/2022 | Always | Major | Everytime | Medium | Book Ticket | To Be Fixed | Open |  | Khiêm | Tài

## Bug Screenshot
ID#16
BugID#17
Bug ID# 13
Bug ID#22
Bug ID#23
Bug ID 31

## Data
Build | Feature | Bug Resolution | Severity | Frequency | Priority | TC Status
0.9.8 | Register | New | Critical | Everytime | Urgent | Open
0.9.9 | Login | To Be Distributed | Major | Sometimes | High | Closed
1.0.0 | View Ticket | To Be Fixed | Minor | Hardly | Medium
| Book Ticket | Need More Information |  |  | Low
| My Ticket | Not Reproducible
| My Account | Fixed
| Other | Not a Problem
Duplicate
Deferred
Feature Limitation
Passed Verification
Failed Verification